## Sheet2
Quarter | Week | Task | Difficulty | Estimated Time (Weeks) | Actual Time (Weeks) | Status | Notes
Q1 | 1-2 | Set up Git repository with proper branching strategy | Low | 2
Q1 | 1-2 | Choose CI/CD platform and configure basic pipeline | Medium | 2
Q1 | 3-4 | Implement unit and integration tests | Medium | 2
Q1 | 3-4 | Implement code linting and static analysis | Low | 1
Q1 | 5-6 | Create Dockerfile and build container image | Medium | 2
Q1 | 5-6 | Implement automated build and packaging | Medium | 2
Q1 | 7-8 | Set up development environment with CI/CD integration | Low | 1
Q1 | 7-8 | Conduct initial testing of CI/CD pipeline | Medium | 1
Q2 | 9-10 | Implement basic deployment to a development environment | Medium | 2
Q2 | 9-10 | Implement basic monitoring and logging for the application | Medium | 2
Q2 | 11-12 | Improve test coverage and stability | Medium | 2
Q2 | 11-12 | Refine CI/CD pipeline based on initial testing results | Medium | 2
Q2 | 13-14 | Implement deployment to a testing environment | Medium | 2
Q2 | 13-14 | Implement more advanced monitoring and alerting | Medium | 2
Q2 | 15-16 | Conduct user acceptance testing (UAT) of the application in the testing environment | Low | 1
Q2 | 15-16 | Gather feedback and iterate on the CI/CD pipeline based on UAT results | Low | 1
Q3 | 17-18 | Implement deployment to a production environment | High | 2
Q3 | 17-18 | Implement robust rollback and recovery mechanisms | Medium | 2
Q3 | 19-20 | Implement blue/green deployments or other advanced deployment strategies | High | 2
Q3 | 19-20 | Integrate with existing monitoring and alerting systems | Medium | 2
Q3 | 21-22 | Conduct thorough production monitoring and performance testing | Medium | 2
Q3 | 21-22 | Optimize CI/CD pipeline for faster build and deployment times | Medium | 2
Q3 | 23-24 | Document and train the development team on the CI/CD process | Low | 1
Q3 | 23-24 | Conduct a post-implementation review and gather feedback | Low | 1
Q4 | 25-26 | Implement automated security scanning and vulnerability checks | Medium | 2
Q4 | 25-26 | Integrate with incident response and remediation processes | Medium | 2
Q4 | 27-28 | Implement canary deployments and A/B testing for new features | High | 2
Q4 | 27-28 | Improve the CI/CD pipeline's scalability and maintainability | Medium | 2
Q4 | 29-30 | Implement self-healing capabilities for the CI/CD pipeline | High | 2
Q4 | 29-30 | Continuously monitor and improve the CI/CD pipeline's performance and efficiency | Low | 2
Q4 | 31-32 | Conduct a quarterly review of the CI/CD process and identify areas for improvement | Low | 1
Q4 | 31-32 | Plan and prioritize future enhancements to the CI/CD pipeline | Low | 1